Add Dependencies for Activities

Date:3/Feb/2026

Project Title: 	FixIt Jo - A Mobile Application for Connecting Users with Local Craftsmen Using GPS and AI Chatbot

Task 2: Add Dependencies for Activities

| Activity ID | Activity Name | Predecessor(s) | Dependency Type |
| --- | --- | --- | --- |
| 1.1.1 | Define project objectives | - | - |
| 1.1.2 | Develop timeline | 1.1.1 | FS |
| 1.1.3 | Allocate resources | 1.1.2 | FS |
| 1.2.1 | Schedule meetings | 1.1.3 | FS |
| 1.2.2 | Define team roles | 1.1.3 | FS |
| 1.3.1 | Track task completion | 1.2.1, 1.2.2 | FS |
| 1.3.2 | Prepare status reports | 1.3.1 | SS |
| 1.3.3 | Update dashboard | 1.3.1 | SS |
| 2.1.1 | Interview stakeholders | 1.1.3 | FS |
| 2.1.2 | Collect requirements | 2.1.1 | FS |
| 2.2.1 | Write user stories | 2.1.2 | FS |
| 2.2.2 | Prioritize user stories | 2.2.1 | FS |
| 2.3.1 | Analyze technical feasibility | 2.1.2 | FS |
| 2.3.2 | Analyze financial feasibility | 2.3.1 | FS |
| 2.3.3 | Define project scope | 2.2.2, 2.3.2 | FS |
| 3.1.1 | Draw Use Case diagrams | 2.3.3 | FS |
| 3.1.2 | Draw Sequence diagrams | 3.1.1 | FS |
| 3.1.3 | Draw DFD diagrams | 3.1.1 | FS |
| 3.1.4 | Draw ER diagrams | 3.1.1 | FS |
| 3.2.1 | Define database schema | 3.1.4 | FS |
| 3.2.2 | Define tables | 3.2.1 | FS |
| 3.3.1 | Design wireframes | 3.1.1 | FS |
| 3.3.2 | Create mockups | 3.3.1 | FS |
| 3.4.1 | Define system components | 3.1.2, 3.1.3 | FS |
| 3.4.2 | Define communication | 3.4.1 | FS |
| 4.1.1 | Login functionality | 3.2.2 | FS |
| 4.1.2 | Registration functionality | 3.2.2 | FS |
| 4.1.3 | Password recovery | 4.1.1 | FS |
| 4.2.1 | Create profile | 4.1.2 | FS |
| 4.2.2 | Edit profile | 4.2.1 | FS |
| 4.2.3 | View profile | 4.2.1 | FS |
| 4.3.1 | Create service request | 4.2.1, 3.3.2 | FS |
| 4.3.2 | Assign technician | 4.3.1 | FS |
| 4.3.3 | Track service status | 4.3.2 | FS |
| 4.4.1 | Integrate GPS API | 3.4.2 | FS |
| 4.4.2 | Display on map | 4.4.1 | FS |
| 4.5.1 | Integrate chatbot API | 3.4.2 | FS |
| 4.5.2 | Define chatbot scripts | 4.5.1 | FS |
| 4.6.1 | Implement messaging | 3.4.2 | FS |
| 4.6.2 | Implement notifications | 4.6.1 | FS |
| 5.1.1 | Test individual modules | 4.1.3, 4.2.3, 4.3.3, 4.4.2, 4.5.2, 4.6.2 | FS |
| 5.2.1 | Test module interactions | 5.1.1 | FS |
| 5.3.1 | Test system end-to-end | 5.2.1 | FS |
| 5.4.1 | Gather user feedback | 5.3.1 | FS |
| 5.4.2 | Validate requirements | 5.4.1 | FS |
| 6.1.1 | Write technical docs | 1.1.1 | SS |
| 6.1.2 | Prepare diagrams | 3.1.4 | SS |
| 6.2.1 | Create user guide | 5.4.2 | FS |
| 6.2.2 | Add screenshots | 6.2.1 | FS |
| 6.3.1 | Prepare presentation | 5.4.2, 6.1.1, 6.2.2 | FS |
| 6.3.2 | Conduct demo | 6.3.1 | FS |