Develop a network diagram

Date:4/Feb/2026

Project Title: FixIt Jo - A Mobile Application for Connecting Users with Local Craftsmen Using GPS and AI Chatbot

Task 3 and Task 4:

| 0 | 3 days (planning) | 3 |
| --- | --- | --- |
| 0 | 0 | 3 |

Develop a network diagram and perform backward and forward pass then find critical path

| 3 | 7 days (requirement) | 10 |
| --- | --- | --- |
| 3 | 0 | 10 |

| 10 | 8 days (design) | 18 |
| --- | --- | --- |
| 10 | 0 | 18 |

| 18 | 3 days (auth) | 21 |
| --- | --- | --- |
| 22 | 4 | 25 |

| 18 | 3 days (profile) | 21 |
| --- | --- | --- |
| 22 | 4 | 25 |

| 18 | 7 days (service) | 25 |
| --- | --- | --- |
| 18 | 0 | 25 |

| 25 | 4 days (Messaging) | 29 |
| --- | --- | --- |
| 25 | 0 | 29 |

| 29 | 12 days (testing) | 41 |
| --- | --- | --- |
| 29 | 0 | 41 |

| 41 | 3days (final) | 44 |
| --- | --- | --- |
| 41 | 0 | 44 |

Critical path: is the tallest bath in the diagram

1 Planning → 2 Requirements → 3 Design → 4.3 Service → 4.6 Messaging →

5 Testing → 6.0 Final Presentation

Total Duration: 44 days