Estimate Time and Effort

Date 3/Feb/2026

Project Name: FixIt Jo - Mobile Application for Connecting Users with Local Craftsmen

| WBS # | Activity Name | Duration | Effort (Person-Days) |
| --- | --- | --- | --- |
| 1.0 | Project Management | Ongoing | 20 |
| 1.1.1 | Define objectives | 1 day | 1 |
| 1.1.2 | Develop timeline | 1 day | 1 |
| 1.1.3 | Allocate resources | 0.5 day | 1 |
| 1.2.1 | Schedule meetings | 0.5 day | 1 |
| 1.2.2 | Define team roles | 0.5 day | 1 |
| 1.3.1-3 | Tracking (ongoing) | Throughout | 15 |
| 2.0 | Requirements & Analysis | 7 days | 21 |
| 2.1.1 | Interview stakeholders | 2 days | 3 |
| 2.1.2 | Collect requirements | 2 days | 4 |
| 2.2.1 | Write user stories | 1 day | 2 |
| 2.2.2 | Prioritize stories | 0.5 day | 1 |
| 2.3.1 | Technical feasibility | 1 day | 2 |
| 2.3.2 | Financial feasibility | 1 day | 2 |
| 2.3.3 | Define scope | 1 day | 2 |
| 3.0 | System Design | 8 days | 24 |
| 3.1.1 | Use Case diagrams | 1.5 days | 3 |
| 3.1.2 | Sequence diagrams | 1 day | 2 |
| 3.1.3 | DFD diagrams | 1 day | 2 |
| 3.1.4 | ER diagrams | 1.5 days | 3 |
| 3.2.1 | Database schema | 1 day | 2 |
| 3.2.2 | Tables & relationships | 1 day | 2 |
| 3.3.1 | Design wireframes | 1.5 days | 3 |
| 3.3.2 | Create mockups | 2 days | 4 |
| 3.4.1 | System components | 1 day | 2 |
| 3.4.2 | Component communication | 0.5 day | 1 |
| 4.0 | Implementation | 15 days | 45 |
| 4.1.1 | Login functionality | 1 day | 2 |
| 4.1.2 | Registration | 1 day | 2 |
| 4.1.3 | Password recovery | 0.5 day | 1 |
| 4.2.1 | Create profile | 1 day | 2 |
| 4.2.2 | Edit profile | 0.5 day | 1 |
| 4.2.3 | View profile | 0.5 day | 1 |
| 4.3.1 | Create service request | 2 days | 4 |
| 4.3.2 | Assign technician | 1.5 days | 3 |
| 4.3.3 | Track status | 1.5 days | 3 |
| 4.4.1 | Integrate GPS API | 2 days | 4 |
| 4.4.2 | Display on map | 1.5 days | 3 |
| 4.5.1 | Integrate chatbot API | 2 days | 4 |
| 4.5.2 | Define scripts | 1.5 days | 3 |
| 4.6.1 | Implement messaging | 2 days | 4 |
| 4.6.2 | Push notifications | 1.5 days | 3 |
| 5.0 | Testing & QA | 12 days | 24 |
| 5.1.1 | Unit testing | 3 days | 6 |
| 5.2.1 | Integration testing | 3 days | 6 |
| 5.3.1 | System testing | 3 days | 6 |
| 5.4.1 | User feedback | 2 days | 4 |
| 5.4.2 | Validate requirements | 1 day | 2 |
| 6.0 | Documentation & Presentation | Throughout + 3 final | 40 |
| 6.1.1 | Write technical docs | Throughout project | 25 |
| 6.1.2 | Prepare diagrams | Throughout project | 8 |
| 6.2.1 | Create user guide | 2 days | 3 |
| 6.2.2 | Add screenshots | 1 day | 2 |
| 6.3.1 | Prepare presentation | 2 days | 4 |
| 6.3.2 | Conduct demo | 1 day | 2 |